KAFCO INVENTORY CYCLE

& REORDER WINDOW ANALYTICS

A Data-Driven Spare Parts Procurement Model for Multi-Year Maintenance Shutdown Cycles

Prepared by: Mir Al Musaddek

Based on Industrial Attachment at Karnaphuli Fertilizer Company (KAFCO), Bangladesh

Tools: Microsoft Excel · PostgreSQL · Tableau Public

Report Date: July 2026

Data Disclosure: This project uses a synthetically generated dataset (400 records) modeled on realistic KAFCO procurement patterns and industry-standard spare parts categories. Real operational data was not available for this attachment. All figures, dates, and item codes are simulated for portfolio and learning purposes and do not represent actual KAFCO records or vendor performance.

# 1. Executive Summary

KAFCO's spare-parts procurement for major maintenance shutdowns spans multi-year lead times, yet purchase orders have historically been triggered without a structured, data-backed timeline. This project builds a reorder-window model that converts historical procurement records into a category-specific purchase order calendar, and separately identifies which spare-part categories are over-stocked relative to consumption ahead of the next shutdown.

Working from a 400-item synthetic dataset spanning 10 spare-part categories and four historical shutdown cycles (2017–2027), the analysis produced two outputs: (1) a consumption velocity classification for every item, and (2) a recommended purchase-order date per category.

## Headline Findings

- The next major shutdown is targeted for 10-Sep-2027. Mechanical and Piping — the two categories with the longest and most variable lead times — require purchase orders 6+ months before shutdown (14-Dec-2026 and 03-Mar-2027 respectively) to arrive on time at a 95% service level.

- 37.5% of Mechanical spare parts and 100% of Civil parts fall into the Slow-Moving velocity tier, indicating capital tied up in inventory that turns over far less than once per year — a candidate for inventory rationalization.

- Across the full 400-item dataset, 33.2% of items are classified Slow-Moving, 33.3% Medium-Moving, and 33.5% Fast-Moving (split by turnover rate) — the classification is functioning as designed, evenly separating the catalogue into actionable tiers.

- Lead time variability (coefficient of variation) is highest for shutdown-linked categories, justifying safety buffers ranging from 23 days (Lubrication) to 76 days (Mechanical) — buffers are data-derived, not a flat assumption.

- Benchmarked against a common non-analytical heuristic — a flat "order 90 days before shutdown" rule — the data-driven model closes a stockout-risk exposure that would otherwise affect 95% of the catalogue (380 of 400 items), arriving a weighted average of 103 days late and up to 179.8 days late for Mechanical (Section 5).

# 2. Project Objectives

Two objectives were defined at the outset:

- Consumption Velocity — determine how quickly each spare-part category is consumed relative to the multi-year (3–4 year) shutdown cycle, to separate routine-use stock from shutdown-reserve stock.

- Optimal Reorder Windows — calculate, per category, the exact calendar date by which a purchase order must be placed so that the part arrives at the warehouse before the next shutdown begins, using the formula:

Reorder Date  =  Shutdown Date  –  Average Lead Time (per category)  –  Safety Buffer

# 3. Data Source & Methodology

## 3.1 Dataset

A synthetic dataset of 400 items across 10 categories (Mechanical, Electrical, Instrumentation, Piping, Safety, Chemical, Utility, Lubrication, HVAC, Civil) was constructed with realistic industrial assumptions rather than randomized values:

- Shutdown-linked categories (Mechanical, Piping, Instrumentation, Civil) were assigned long lead times (90–270 days) and issue dates clustered within 3 weeks of a shutdown date — mirroring how plants stage critical spares ahead of planned outages.

- Routine categories (Electrical, Safety, Chemical, Utility, Lubrication, HVAC) were assigned shorter lead times and issue dates spread 5–60 days after receipt — mirroring continuous operational consumption.

- Four historical shutdown dates were used as anchors: 15-Nov-2017, 01-Mar-2021, 20-Jun-2024, and 10-Sep-2027, reflecting KAFCO's approximate 3.3–3.5 year turnaround cycle.

Seven fields were captured per item: Item Code (anonymized), Category, PO Date, Received Date, Issue Date, Quantity Received, and Demand Rate (units/year) — matching the scope defined in the initial project brief.

## 3.2 Analytical Pipeline

The project was executed as a three-tool pipeline, reflecting a standard industry analytics workflow from raw data to stakeholder-facing dashboard:

| Phase | Tool | Primary Output |
| --- | --- | --- |
| 1. Data Foundation | Microsoft Excel | 400-row synthetic dataset (10 categories); Pivot_summary sheet with COUNTIF/AVERAGEIF/SUMIF aggregations and 2 charts |
| 2. Analysis | PostgreSQL (pgAdmin) | Validation queries; 7 views culminating in kafco_item_detail (400 rows) and kafco_category_kpi (10 rows) |
| 3. Visualization | Tableau Public | 4-worksheet interactive dashboard with filter actions, published dashboard link |
| 4. Distribution | GitHub | Version-controlled repository: /data, /SQL, README with methodology and findings |

## 3.3 Key Calculations

- Cycle segmentation — each item's lifecycle was split into Procurement Days (PO → Received), Storage Days (Received → Issue), and Total Cycle Days (PO → Issue).

- Days of Supply — quantity received ÷ (annual demand rate ÷ 365), giving the theoretical number of days a received batch would last at normal consumption.

- Turnover Rate — annual demand rate ÷ quantity received; used to rank all 400 items and split them into equal Fast / Medium / Slow-Moving tiers via NTILE(3).

- Lead Time Reliability — coefficient of variation (stddev ÷ mean lead time) per category, used to rank supplier predictability.

- Safety Buffer — 1.65 × standard deviation of category lead time, corresponding to a 95% service level — a standard industrial safety-stock formula, not an arbitrary padding figure.

# 4. Findings

## 4.1 Category-Level Reorder Calendar

The table below is the core deliverable: the recommended purchase-order date for each spare-part category ahead of the 10-Sep-2027 shutdown, along with the slow-moving share of each category's inventory.

| Category | Avg Lead Time (days) | Safety Buffer (days) | % Slow-Moving | Recommended PO Date |
| --- | --- | --- | --- | --- |
| Mechanical | 193.8 | 76 | 37.5% | 14-Dec-2026 |
| Civil | 163.7 | 49 | 100.0% | 09-Feb-2027 |
| Piping | 139.8 | 51 | 67.5% | 03-Mar-2027 |
| Instrumentation | 136.5 | 42 | 32.0% | 15-Mar-2027 |
| HVAC | 112.9 | 43 | 13.3% | 07-Apr-2027 |
| Electrical | 109.8 | 42 | 12.5% | 11-Apr-2027 |
| Chemical | 86.9 | 37 | 25.0% | 09-May-2027 |
| Utility | 86.0 | 34 | 40.0% | 13-May-2027 |
| Safety | 63.6 | 30 | 10.0% | 08-Jun-2027 |
| Lubrication | 39.1 | 23 | 15.0% | 10-Jul-2027 |

Rows shaded red under % Slow-Moving (≥35%) — Mechanical (37.5%) and Civil (100%) — carry the dual signal of both a long lead time and low turnover, making them the highest-priority categories for both early procurement action and inventory review.

## 4.2 Consumption Velocity Distribution

Classifying all 400 items by turnover rate produced a near-even three-way split (134 Fast-Moving, 133 Medium-Moving, 133 Slow-Moving), confirming the ranking method is discriminating meaningfully across the catalogue rather than clustering items at one extreme. The category-level pattern is more informative than the aggregate: Civil (100% Slow-Moving) and Piping (67.5%) are almost entirely shutdown-reserve stock, while Electrical (12.5%) and Safety (10%) are overwhelmingly routine-use, fast-turning categories.

Interpretation: categories with a high Slow-Moving share are not necessarily mismanaged — for Civil and Piping this is expected, since these parts exist specifically to be held in reserve for the next shutdown. The risk flag applies where a category shows both a high Slow-Moving share and a low lead time (i.e., stock that could have been ordered later but was received early), which was not observed as a pattern here; long-lead categories and high slow-moving shares track together, consistent with intentional shutdown staging rather than poor planning.

## 4.3 Lead Time & Safety Buffer

Average lead time across all 400 items is 135.3 days (range: 20–270 days). Mechanical parts carry both the longest average lead time (193.8 days) and the largest absolute variability (±45.5 days stddev), driving the largest safety buffer in the dataset (76 days). This compounding effect — long lead time and high variability together — is precisely why Mechanical requires the earliest purchase order of any category, roughly 9 months ahead of shutdown.

# 5. Baseline Comparison & Quantified Impact

A reorder model is only useful if it is measurably better than what a plant would do without it. This section benchmarks the data-driven model (Section 4.1) against two naive procurement rules that are common in plants without formal analytics — a flat calendar rule, and a lead-time calculation that forgets variability. Both are measured in days of schedule risk and SKUs exposed, the only units the dataset can support without unit-cost data. No currency or cost-saving figure is claimed, since the dataset carries no price field — see Section 7, Limitations.

## 5.1 Baseline A — Flat “90 Days Before Shutdown” Rule

A common heuristic in the absence of analytics is to place every purchase order a fixed number of days before a known shutdown date, regardless of category. Using 90 days — a reasonable, frequently-used default — against each category's actual required lead time (average lead time plus safety buffer) shows where that heuristic breaks down:

| Category | Required (Avg Lead + Buffer, days) | Flat Rule (days) | Gap (days) | Status | Items |
| --- | --- | --- | --- | --- | --- |
| Mechanical | 269.8 | 90 | +179.8 | LATE | 120 |
| Civil | 212.7 | 90 | +122.7 | LATE | 15 |
| Piping | 190.8 | 90 | +100.8 | LATE | 40 |
| Instrumentation | 178.5 | 90 | +88.5 | LATE | 50 |
| HVAC | 155.9 | 90 | +65.9 | LATE | 15 |
| Electrical | 151.8 | 90 | +61.8 | LATE | 80 |
| Chemical | 123.9 | 90 | +33.9 | LATE | 20 |
| Utility | 120.0 | 90 | +30.0 | LATE | 20 |
| Safety | 93.6 | 90 | +3.6 | LATE | 20 |
| Lubrication | 62.1 | 90 | −27.9 | EARLY | 20 |

- 9 of 10 categories, covering 380 of 400 items (95.0%), would have their purchase order placed too late under a flat 90-day rule — the part would still be in transit or awaiting receipt when the shutdown begins.

- The exposure is not uniform: Mechanical would arrive 179.8 days after it was needed, versus 3.6 days for Safety — a 50-fold difference in risk that a single flat rule cannot capture.

- Only Lubrication (20 items) would be ordered earlier than necessary under this rule, tying up warehouse space for an extra 27.9 days with no corresponding benefit.

## 5.2 Baseline B — Lead Time Without a Safety Buffer

A subtler and more realistic mistake is calculating average lead time correctly, but omitting the safety buffer for lead-time variability — i.e. ordering exactly “avg lead time before shutdown” and assuming every shipment is on schedule. Because the safety buffer (Section 3.3) exists precisely to absorb that variability, skipping it produces a shortfall equal to the full buffer, in every single category:

| Category | Avg Lead Time Used (days) | Buffer Omitted = Shortfall (days) | Items Under-Ordered |
| --- | --- | --- | --- |
| Mechanical | 193.8 | 76 | 120 |
| Civil | 163.7 | 49 | 15 |
| Piping | 139.8 | 51 | 40 |
| Instrumentation | 136.5 | 42 | 50 |
| HVAC | 112.9 | 43 | 15 |
| Electrical | 109.8 | 42 | 80 |
| Chemical | 86.9 | 37 | 20 |
| Utility | 86.0 | 34 | 20 |
| Safety | 63.6 | 30 | 20 |
| Lubrication | 39.1 | 23 | 20 |

- This mistake affects all 10 categories and all 400 items (100%) by construction — it is a systematic, not occasional, error.

- The item-weighted average shortfall is 51.2 days; the exposure is largest for Mechanical (76 days) because its lead time is also its most variable.

## 5.3 Decision

| Metric | Flat 90-Day Rule | Lead-Time-Only (No Buffer) | Data-Driven Model |
| --- | --- | --- | --- |
| Categories exposed to stockout risk (of 10) | 9 | 10 | 0 |
| Items exposed to stockout risk (of 400) | 380 | 400 | 0 |
| % of catalogue exposed | 95.0% | 100.0% | 0.0% |
| Worst-case days late | 179.8 | 76.0 | 0.0 |
| Item-weighted avg days late (at-risk items) | 103.0 | 51.2 | 0.0 |

The data-driven, per-category model (Section 4.1) is adopted as the procurement calendar for the 10-Sep-2027 shutdown, replacing both naive alternatives. Under either naive baseline, the majority of the catalogue would be ordered with insufficient lead time; under the data-driven model, stockout-risk exposure at the target 95% service level is reduced to zero by design, since each category's PO date is built from its own lead time and variability rather than a shared assumption. The trade-off is operational complexity: a 10-row category calendar to maintain instead of one date, which is a manageable cost for the risk this project quantifies.

# 6. Conclusions

Four conclusions follow directly from the analysis:

- 1. Procurement timing should be category-specific, not uniform. A single blanket lead time assumption (e.g., "order 3 months ahead") would leave Mechanical and Piping parts arriving after they are needed, while over-ordering Lubrication and Safety parts unnecessarily early. The data supports a differentiated PO calendar spanning 14-Dec-2026 (Mechanical) through 10-Jul-2027 (Lubrication) for the same shutdown date.

- 2. Safety buffers should be statistically derived per category, not flat. Buffer sizes in this model range from 23 to 76 days depending on each category's own historical lead time variability — categories with unpredictable suppliers (Mechanical) are protected with a larger buffer than consistent ones (Lubrication), avoiding both stockout risk and unnecessary overstock.

- 3. Against realistic naive alternatives, the model closes a measurable and specific gap. A flat 90-day rule would expose 95% of the catalogue to late delivery (up to 179.8 days late for Mechanical); omitting the safety buffer alone would under-order every category by an average of 51.2 days. Both are quantified failure modes the data-driven model corrects — this is the concrete evidence that the model outperforms plausible non-analytical alternatives, not merely a different way of presenting the same schedule.

- 4. Mechanical and Civil warrant a follow-up inventory review. Their combination of long lead time and high Slow-Moving share means capital is committed early and held for the longest period. This is expected behavior for shutdown-reserve stock, but it is also the segment where excess-quantity ordering would be most costly to correct — a natural next audit target.

## 6.1 Recommendations

- Adopt the category-level reorder calendar (Section 4.1) as the basis for the next PO cycle ahead of the 10-Sep-2027 shutdown, prioritizing Mechanical, Civil, and Piping given their lead time.

- Extend the safety-buffer methodology (Step 8) to future procurement cycles by recalculating lead time variability once each new shutdown's real data becomes available, rather than reusing a fixed figure.

- Validate the model against real KAFCO procurement records when access is available, to confirm the assumed lead-time ranges and shutdown-clustering pattern hold in practice.

- If unit cost data becomes available, extend the Section 5 comparison from days-of-risk to carrying-cost and expedite-freight cost, to translate the current schedule-risk finding into a currency figure.

# 7. Limitations

- The dataset is synthetic. Real supplier lead times, demand rates, and shutdown-linked ordering behavior at KAFCO may differ from the modeled assumptions, so absolute dates and buffer sizes should be treated as a methodology demonstration rather than an operational schedule.

- The safety-stock formula (1.65σ, 95% service level) assumes lead time variability is approximately normally distributed; this was not tested against the synthetic data's actual distribution shape.

- Demand rate is treated as constant per item; no seasonality or shutdown-driven demand spikes were modeled beyond the issue-date clustering built into the dataset.

- The Section 5 baseline comparison is measured in schedule-risk days and SKU counts, not currency, because the dataset has no unit-cost or carrying-cost field. Any cost-saving figure would be an assumption, not a finding, and has been deliberately excluded.

# 8. Deliverables

- Phase 1 (Excel): KAFCO_ItemCode_Category_Dates_400.xlsx — 400-row source dataset with Pivot_Summary sheet.

- Phase 2 (SQL): KAFCO_full_analysis.sql — PostgreSQL script; kafco_item_detail (400 rows) and kafco_category_kpi (10 rows) export views.

- Phase 3 (Tableau): KAFCO Inventory Cycle & Reorder Analytics — published interactive dashboard (4 linked worksheets: Velocity Breakdown, Turnover by Category, Reorder Timeline, Slow-Moving Risk).

- Phase 4 (GitHub): Version-controlled repository with /data /SQL folders and README documenting methodology, assumptions and findings.

- Baseline comparison workbook: KAFCO_Baseline_Comparison.xlsx — live-formula worksheet reproducing every figure in Section 5, for verification or re-use with real data.